## Sheet1
Questions | Comments | Status
There is no facility to add an Ad Hoc intervention. This is essential. | This functionality is already implemented and had permission only for Administrator for adding Adhoc Intervention
There should be a facility to create an intervention, and to upload forms not included in the App | Addition of fileUpload in Add AdHoc Intervention after Recurrence Time | Change Request
How do we archive a resident if they leave, or if they die? | Have to add Leaving Date of Resident and Reason for Leaving coloumns in database and if the leaving date of Resident was included then after that day the Resident must be in inactive state. | Change Request
Summary should include personal information, preferences, consent and End of Life | If we include personal information, preferences, consent and End of Life the Summary will contain lot of data | Change Request
How do we archive or delete prospective resident if entered incorrectly or referral closed and not admitted? | Have to add Leaving Date of Prospect and Reason for Leaving coloumns in database and if the leaving date of Prospect was included then after that day the Prospect must be in inactive state. | Change Request
There should be a free text option on all interventions so that the assessor can input any relevant information not included in the questions. | Have to add FreeText while generating Interventions. | Change Request
Patterns could be simplified by adding a Twice a day, Three times a day, Four times a day and If ticked schedule as follows: Twice a day 9am and 5pm, Three times a day 9am, 1pm, 5pm, Four times a day 9am, 1pm, 5pm, 9pm | As of now we can generate interventions any number of times per a day
Patterns should have an option for 'ongoing until review', and then review triggered monthly | To be taken to next version
ABC charts should be able to be added Ad Hoc | What are ABC charts? | Need to be clarified
ABC charts should only be triggered in an intervention when a behaviour or incident has been logged. | What are ABC charts? | Need to be clarified
In personal information add: NHS number, Date of Admission, Admitted from, Brief description of past and present medical history and diagnosis | Have to add the columns in the database and have to add NHS NHS number, Date of Admission, Admitted from, Brief description of past and present medical history and diagnosis in personal Information | Change Request
Once accepted add intervention: Property List. this should enable the carer to list all of the person’s property and be available to view and print on request | Change Request=>Ouside the scope
Capacity:There should be an option at the end: Are there Capacity issues that require further assessment? If Yes trigger Intervention: professional referral. | Have to add the question at the end of the capacity section. | Change Request
There should be an add hoc intervention: Professional visit. this should enable free text so that carer can add details of visit. All professional visits should be available as a report for the individual resident. date and time of visit should be included in hand over and daily notes | Have to add the freetext in Add Adhoc Intervention and the the individual date and time of visit must shown in the Daily Dairy and Handover Notes | Change Request
There should be an option on each intervention when complete to ‘add to hand over notes’ yes or no. Not every intervention needs to be added to hand over notes. However each intervention needs to be added to the daily notes for each individual resident. these should be available to view and print if required | When clicking on the Intervention in the popup have to add RadioButton Add to HandoverNotes.If yes only we have to add to the HandOverNotes | Change Request
Admin Dashboard should include: interventions not completed, reviews due, falls, incidents, occupancy, admissions, potential residents | Report 1
A rolling ‘Facebook’ type feed, showing interventions completed over the day and previous two days would be a good addition. This does not need to be archived or saved. | Report 2
Carers need to review hand over notes before starting shift, so will need to confirm that notes read and understood before the rest of the App becomes available | For the carer first time login we have to show only HandOverNotes And we have a alert that notes read and understood if 'Yes' only we have start rest of the App | Change Request
This should be a ‘pop up’ during the assessment stage, when identified through the assessment. the assessment should not continue until this has been addressed or actioned | As of now we are showing the popup and in the summary
States number of carers 1 but does not state for what activity. Useless without that information | Add the parent Question | Change Request
State what PRN medication is prescribed and what for | It is a Yes/No question=>Please send more information | Need to be clarified
Pain Monitoring | Please specify the parts which are to be highlighted. | Need to be clarified